## Test Cases
Product Name |  | Motion View | TC Start Date | 18/06/2022 | TC Execution Start Date | 18/06/2022 | TEST CASE SUMMARY
Module Name |  | Sign Up (Andriod) | TC End Date | 22/06/2022 | TC Execution End Date | 22/06/2022 | PASS | 19
Epic |  | N/A | Test Case Developed By | Md. Sakib Shahriar | Browser (tested) | 0 | FAIL | 13
Developer Name (TL) |  | x | Test Case Reviewed By | Sabiul Islam Rashed | Performance (tested) | No | WARNING | 2
Test Executed by | [6 empty] | TOTAL | 34
Test Case ID/Name | Test Case Description | precondition | Test Data | Step Description | Expected Result | Actual | Status | Remarks | comm
TC001-Signup Account | Valid name field check | … | Full Name = Shakib Hasan | 1. Download and install Motion View App form Play Store 2. Tap to the Motion View App incon and then tap to Account icon 3. Then Tap to Login button and scroll down and tap on Sign up 4. Enter valid full name 5. Fill up the others valid information 6. Tap on Signup button | Should register the account successfully | Registration Successful | PASS | Successful Registration
TC002-Signup Account | Invalid Name field check | … | Full Name = 1S@k!8 Sh#52*+/~& | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter invalid name containing numbers and special characters 4. Fill up the others valid information 5. Tap on Signup button | Shouldn’t take the invalid name and the user should get a pop-up alert for an invalid name | Takes invalid name and sends OTP for account creation | FAIL | Invalid Name
TC003-Signup Account | Empty Name Field check | … | Full Name = | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Keep the name field empty 4. Full up the others valid information 5. Tap on Signup button | Shouldn’t complete registration without name field and the user should get a pop-up alert for the empty name field | The user gets a pop-up alert for empty name field which says 'Empty Field! Please fill the empty field!' and registration can not be completed | PASS | Empty Name Field
TC004-Signup Account | Empty Phone Number Field check | … | Phone = | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Keep the phone number field empty 4. Full up the others valid information 5. Tap on Signup button | Registration should not be completed and the user should get a pop-up alert for empty Phone number field | The user gets a pop-up alert for empty Phone no field which says 'Empty Field! Please fill the empty field!' and registration can not be complete | PASS | Empty Phone Number Field
TC005-Signup Account | Phone Number Field check with more than 11 digits | … | Phone = 017664896592 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter invalid phone number containing more than 11 digits 4. Full up the others valid information 5. Tap on Signup button | Shouldn’t take the invalid phone no, the user should get a pop-up alert for invalid phone no and registration should not be complete | The user gets a pop-up alert for Invalid Phone no that says 'Invalid Phone No. Please provide a valid phone no.' and registration can not be complete | PASS | Invalid Phone Number (More than 11 digits)
TC006-Signup Account | Phone Number Field check with any digits with total 11 digits | … | Phone = 17201122151 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter invalid phone number which can start with any digits and total 11 digits. 4. Full up the others valid information 5. Tap on Signup button | Shouldn’t take the invalid phone no, the user should get a pop-up alert for invalid phone no starting without 01 and OTP should not be sent to invalid number | Takes invalid phone number which starts without 01 and sent OTP to invalid number | FAIL | Invalid Phone Number Without starting 01
TC007-Signup Account | Phone Numbe Field check starting with 010 | … | Phone = 01089967114 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter invalid phone number which starts with 010 4. Full up the others valid information 5. Tap on Signup button | Shouldn’t take the invalid phone no and the user should get a pop-up alert for invalid phone no and OTP should not be sent to invalid number | Takes invalid phone number which starts with 010 and sent OTP to invalid number | FAIL | Invalid Phone Number Starts with 010
TC008-Signup Account | Phone Numbe Field check starting with 012 | … | Phone = 01289967114 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter invalid phone number which starts with 012 4. Full up the others valid information 5. Tap on Signup button | Shouldn’t take the invalid phone no and the user should get a pop-up alert for invalid phone no and OTP should not be sent to invalid number | Takes invalid phone number which starts with 012 and sent OTP to invalid number | FAIL | Invalid Phone Number Starts with 012
TC009-Signup Account | Phone Numbe Field check starting with 011 | … | Phone = 01166489654 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter invalid phone number which starts with 011 4. Full up the others valid information 5. Tap on Signup button | Shouldn’t take the invalid phone no and the user should get a pop-up alert for invalid phone no and OTP should not be sent to invalid number | Takes invalid phone number which starts with 011 and sent OTP to invalid number | FAIL | Invalid Phone Number Starts with 011
TC010-Signup Account | Phone Number Field check with less than 11 digits | … | Phone = 0168996711 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter invalid phone number containing less than 11 digits 4. Full up the others valid information 5. Tap on Signup button | Shouldn’t take the invalid phone no and the user should get a pop-up alert for invalid phone no and registration should not be complete | The user gets a pop-up alert for Invalid Phone no that says 'Invalid Phone No. Please provide a valid phone no.' and registration can not be complete | PASS | Invalid Phone Number (Less than 11 digits)
TC011-Signup Account | Phone Number Field check starts with + | … | Phone = +0168996711 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter invalid phone number which starts with '+' (total 11 character) 4. Full up the others valid information 5. Tap on Signup button | Shouldn’t take the invalid phone no and the user should get a pop-up alert for invalid phone no and registration should not be complete | Takes invalid phone number which starts with + and sent OTP to invalid number | FAIL | Invalid Phone Number Starting with +
TC012-Signup Account | Empty Email Field check | … | Email = | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Keep the Email field empty 4. Full up the others valid information 5. Tap on Signup button | Shouldn’t complete registration without email field and the user should get a pop-up alert for empty email field | OTP successfully sent to the given number for registration while the email field was empty | FAIL | Empty Email Field
TC013-Signup Account | Invalid Email field check | … | Email = xYzDfghS#1@~+/¦^$dgmail.com | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter invalid email containing numbers and special characters before and after @ 4. Fill up the others valid information 5. Tap on Signup button | Shouldn’t take the invalid email, the user gets a pop-up alert for invalid email and OTP should not be sent and therefore registration should not be complete | The user gets a pop-up alert for invalid email format and says 'Invalid Email Please provide a valid email address' | PASS | Invalid Email
TC014-Signup Account | Invalid Email field check | … | Email = xYzDfghS#1^$%¦#@gmail.com | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter invalid email containing numbers and special characters before @ 4. Fill up the others valid information 5. Tap on Signup button | Shouldn’t take the invalid email, the user gets a pop-up alert for invalid email and OTP should not be sent and therefore registration should not be complete | Takes invalid email, Successfully sends OTP, and Creates an account with an invalid email | FAIL | Invalid Email
TC015-Signup Account | Email Field Check without symbol '@' | … | Email = sakib23gmail.com | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter invalid email without containing '@' 4. Fill up the others valid information 5. Tap on Signup button | Shouldn't take the invalid email & show a pop-up alert for invalid email | The user gets a pop-up alert for invalid email format and says 'Invalid Email Please provide a valid email address' | PASS | Email Without '@'
TC016-Signup Account | Empty Password Field | … | Password = | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Keep the password field empty 4. Full up the others valid information 5. Tap on Signup button | Shouldn’t complete registration without password, the user should get a pop-up alert for empty password field | The user gets a pop-up alert for empty 'password' field that says 'Empty Field Please fill the empty field!' | PASS | Empty Password Field
TC017-Signup Account | Empty Confirm Password Field | … | Confirm Password = | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Keep the confirm password field empty 4. Full up the others valid information 5. Tap on Signup button | Shouldn’t complete registration without 'confirm password' field and the user should get a pop-up alert for empty 'confirm password' field | The user gets a pop-up alert for empty 'confirm password' field that says 'Empty Field Please fill the empty field!' | PASS | Empty Confirm Password Field
TC018-Signup Account | Check for Password and Confirm Password Match | … | Password = sakib786 Confirm Password = sakib786 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter valid password and confirm password 4. Full up the others valid information 5. Tap on Signup button | Should send OTP for completing the registration | Successfully sent OTP for completing the registration | PASS | Password Match Check
TC019-Signup Account | Check for Password and Confirm Password Mismatch | … | Password = sakib123 Confirm Password = sakib122 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter password and confirm password but both must not be the same 4. Full up the others valid information 5. Tap on Signup button | Users should get a pop-up alert for password mismatch | The user gets a pop-up alert for password mismatch which says 'Password not matched! Please provide same password!' | PASS | Password Mismatch Check
TC020-Signup Account | Check for single character Password acceptance | … | Password = 1 Confirm Password = 1 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter password and confirm password but with 1 character and must be same 4. Full up the others valid information 5. Tap on Signup button | Users should get a pop-up alert for too short password and the minimum password length should be 8 | The user gets a pop-up alert that says 'Invalid Password Minimum password length is 5' | WARNING | Password Acceptance Check (Single character)
TC021-Signup Account | Check Password acceptance for 4 characters | … | Password = h21# Confirm Password = h21# | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter password and confirm password but with 4 characters and must be same 4. Full up the others valid information 5. Tap on Signup button | Users should get a pop-up alert for too short password and the minimum password length should be 8 | The user gets a pop-up alert that says 'Invalid Password Minimum password length is 5' | WARNING | Password Acceptance Check (4 characters)
TC022-Signup Account | Weak Password Acceptance check | … | Password = 12345 Confirm Password = 12345 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter password and confirm password but with weak passwords containing only numeric characters 4. Full up the others valid information 5. Tap on Signup button | Users should get a pop-up alert for too short password and the minimum password length should be 8 | Accepts weak password and send successfully send OTP for completing the registration | FAIL | Weak Password Accepttance
TC023-Signup Account | Strong Password Acceptance check | … | Password = sZ2s_&d!/X>,$#Y Confirm Password = sZ2s_&d!/X>,$#Y | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter password and confirm password containing upper and lower case letters, Non-alphanumeric characters, special characters and Numberaic characters 4. Full up the others valid information 5. Tap on Signup button | Should send OTP for completing the registration | Accepts strong password and send successfully send OTP for completing the registration | PASS | Strong Password Acceptance
TC024-Signup Account | Weak Password Acceptance check | … | Password = abcde Confirm Password = abcde | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter password and confirm password but with weak passwords containing only alphabetic characters 4. Full up the others valid information 5. Tap on Signup button | Users should get a pop-up alert for too weak password and the minimum password length should be 8 | Accepts weak password and sent successfully send OTP for completing the registration | FAIL | Weak Password Accepttance
TC0025-Signup Account | Weak Password Acceptance check | … | Password = abcd123 Confirm Password = abcd123 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter password and confirm password but with weak passwords containing only alphabetic and numeric characters 4. Full up the others valid information 5. Tap on Signup button | Users should get a pop-up alert for too weak password and the minimum password length should be 8 | Accepts weak password and sent successfully send OTP for completing the registration | FAIL | Weak Password Accepttance
TC026-Signup Account | Invalid OTP field check | Have to fill up all the fields of signup form prior to OTP | OTP = 000000 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Fill up all the fields with valid information 4. Tap on Signup button 5. Enter Invalid OTP | Users should get a pop-up alert for the wrong OTP | Shows pop-up alert for wrong OTP which says 'Error Occurred Failed to verify the OTP!.' | PASS | Invalid OTP
TC027-Signup Account | Resend valid OTP check | Have to fill up all the fields of signup form prior to OTP | OTP = 790227 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Fill up all the fields with valid information 4. Tap on Signup button 5. wait for 1 minute 6. Tap on Re send button 7. Enter new OTP that sent after tapping Re send button | new OTP should be accepted and register account successfully | Successfully accepts new OTP and user registration successful | PASS | Resend OTP
TC028-Signup Account | Resend Invalid OTP check | Have to fill up all the fields of signup form prior to OTP | OTP = 111111 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Fill up all the fields with valid information 4. Tap on Signup button 5. wait for 1 minute 6. Tap on Re send button 7. Enter invalid OTP | Users should get a pop-up alert for the wrong OTP | Shows pop-up alert for wrong OTP which says 'Error Occurred Failed to verify the OTP!.' | PASS | Resend Invalid OTP
TC029-Signup Account | Existing phone number check | … | Phone no = 01879131590 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter a phone number that is already existed 4. Full up the others valid information 5. Tap on Signup button | Users should get a validation message for an already existing phone number | The user gets a validation message that says 'Phone Number Already Exist' | PASS | Existing Phone Number
TC030-Signup Account | Existing Email check | … | Email = sakibhasan21@gmail.com | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter an email that is already existed 4. Full up the others valid information 5. Tap on Signup button | Users should get a validation message for an already existing email address | The user gets a validation message that says 'Email Already Exist' | PASS | Existing Email
TC031-Signup Account | Invalid Name field check | … | Full Name = S | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Fill up the Full Name field with only one character 4. Fill up the others valid information 5. Tap on Signup button | Shouldn’t take the invalid name and the user should get a pop-up alert for an invalid name | Takes invalid name and sends OTP for account creation | FAIL | Invalid Name(Single Character)
TC032-Signup Account | Invalid Email field check | … | Email = sakibezio23@gmail. | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter invalid email without email domain 4. Fill up the others valid information 5. Tap on Signup button | Shouldn’t take the invalid email, the user gets a pop-up alert for invalid email and OTP should not be sent and therefore registration should not be complete | The user gets a pop-up alert for invalid email format that says 'Invalid Email Please provide a valid email address' | PASS | Invalid Email Format (without Email Domain)
TC033-Signup Account | Check for OTP Time Limit | Have to fill up all the fields of signup form prior to OTP | OTP = 404036 | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Fill up all the fields with valid information 4. Tap on Signup button 5. Enter the valid OTP after waiting for 5 minutes | Shouldn't take the valid OTP after 3 minutes and the user should get a pop-up alert for the wrong OTP | Doesn't take the valid OTP after 3 minutes and the user gets a pop-up alert that says 'Error Occurred Failed to verify the OTP!.' | PASS | OTP Time Limit Check
TC034-Signup Account | Phone Number Field check with any 11 characters | … | Phone = A10f%&*_(/~ | 1. Tap to the Motion View App incon and then tap to Account icon 2. Then Tap to Login button and scroll down and tap on Sign up 3. Enter invalid phone number containing a total 11 number of any characters 4. Full up the others valid information 5. Tap on Signup button | Shouldn’t take any input except numbers and the user should get a popup alert for an invalid phone no and OTP should not be sent to an invalid number | Takes invalid phone number which contains any type of 11 characters and sends OTP to an invalid number | FAIL | Phone number with any 11 characters